## Product backlog
PRODUCT BACKLOG Data
ID | Feature | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | ​Show in a bar chart the 5 neighborhoods with the biggest amount of bike containers (​fietstrommels​). | M | doing | doing
1 | Show in a line chart the amount of stolen bicycles per month. | M |  | doing
2 | Show the amount of stolen bicycles and amount of installed bike containers per month given a specific neighborhood through a grouped bar chart. The neighborhood should be selected by the user. | M |  | doing
3 | Show in two pie charts the distribution of most stolen bike brands and colors. | M |  | doing
4 | only mobile version​: Save the current location of your bike in the note app. Note​: your application must be capable of writing the note without explicitly opening the note app. | M |  | doing
5 | only mobile version​: Create a reminder/appointment in the agenda about when to pick up the bike from a specific location. ​ Note​ : Your application must be capable of putting the appointment in the agenda without explicitly opening the agenda application. | M
6 | Show on a map the amount of thefts per neighbourhood, by coloring the neighbourhood differently (shades of red/orange/yellow/green) based on the thefts amount. The border between neighbourhoods must be (somehow) clear. | S
7 | Show the location and route indication to the closest bike container to the user, given his/her current position. | S
8 | Create a database | M | doing | done
9

## Sprint 1
SPRINT BACKLOG
ID | User story | Priority | Time Estimation | Tasks | acceptance criteria
0 | As a user, I want to see a bar chart of the 5 neighborhoods with the biggest amount of bike containers, so I can see wich neighborhoods have te most bike containers. | M | 12 | >Create a grid. >Determine what the difference in values should be for a graph where you can read information from. >Create axis with names and values at crossing point. >Create a dynamic legend. | >The bar chart shows the input data correct. >The bar chart has an acceptable minimum and maximum, relative to the values of the bar. (At least 75% of the horizontal axis is used with the line chart and at least 50% of the vertical axis is used with the bar chart) >There is a legend, that gives information about the bars. >Both the x-axis and y-axis have a name.
8 | As a developer, I want a datbase localy so I can easily retrieve data and use it in the app | M | 16 | >Find out how to use a database for an android app. >Develop a program that is able to get information out of a excel file and places it into a database. >Run the created parcer. | >The data is correctly converted into values usefull for the graphs. >The database is designed in a way, that it can be used by different accounts.

## Sprint 2
SPRINT BACKLOG
ID | User story | Priority | Time Estimation | Tasks | acceptance criteria
0 | As a user, I want to see a bar chart of the 5 neighborhoods with the biggest amount of bike containers, so I can see wich neighborhoods have te most bike containers. | M | 12 | >Create code that retrieves data from the databases. >Create a filter checklist in the app where the user can select the data that he want to see in a selected chart type. >Generate a bar chart. | >The bar chart shows the input data correct. >The bar chart has an acceptable minimum and maximum, relative to the values of the bar. (At least 75% of the horizontal axis is used with the line chart and at least 50% of the vertical axis is used with the bar chart) >There is a legend, that gives information about the bars. >Both the x-axis and y-axis have a name.
1 | As a user, I want to see a line chart of the amount of stolen bicycles per month, so I can see wich month has te most stolen bicycles. | M | 12 | >Create code that retrieves data from the databases. >Create a filter checklist in the app where the user can select the data that he want to see in a selected chart type. >Generate a line chart. | >The line chart shows the input data correct. >The line chart has an acceptable minimum and maximum, relative to the values of the line. (At least 75% of the horizontal axis is used with the line chart and at least 50% of the vertical axis is used with the line chart) >There is a legend, that gives information about the lines. >Both the x-axis and y-axis have a name.
2 | As a user, I want to see the amount of stolen bicycles and amount of installed bike containers per month given a specific neighborhood through a grouped bar chart. The neighborhood should be selected by the user | M | 12 | >Create code that retrieves data from the databases. >Create a filter checklist in the app where the user can select the data that he want to see in a selected chart type. >Generate a bar chart. | >The bar chart shows the input data correct. >The bar chart has an acceptable minimum and maximum, relative to the values of the bar. (At least 75% of the horizontal axis is used with the line chart and at least 50% of the vertical axis is used with the bar chart) >There is a legend, that gives information about the bars. >Both the x-axis and y-axis have a name.
3 | As I user, I want see two pie charts of the distribution of most stolen bike brands and colors, so I can see wich brands and/or colors are most frequently | M | 12 | >Create code that retrieves data from the databases. >Create a filter checklist in the app where the user can select the data that he want to see in a selected chart type. >Generate a pie chart. | >The bar chart shows the input data correct. >The bar chart has an acceptable minimum and maximum, relative to the values of the bar. (At least 75% of the horizontal axis is used with the line chart and at least 50% of the vertical axis is used with the bar chart) >There is a legend, that gives information about the bars. >Both the x-axis and y-axis have a name.
4 | only mobile version: As a user I want to save the current location of my bike in the note app, so I don't forget where my bike is. | M | 16 | >Find out how to get the gps location of the mobile. >Ask for permission for gps, gps has to be on. >Save the location(street/city/coordinates). | >The app saves the correct location. >The app checks if the gps is on. >The app is capable of writing the note without explicitly opening the note app.

## Sprint 3
SPRINT BACKLOG
ID | User story | Priority | Time Estimation | Tasks | acceptance criteria